## Test Counts by Tag
Basic Test Count Information By Tag/Date
A variety of graphs are possible from this data
Note: by “coverage tests” I mean the AA-BG tests, as adapted/improved, and any other tests we add.
Copy from JIRA
Tag | Date | IBM Tests Total | IBM Tests Failing | IBM Tests Working | Coverage Tests Total | Coverage Tests Failing | Coverage Tests Working | Other Junit Tests Total | Other Junit tests Failing | Other Junit tests working | Total Tests | Total Tests Failing | Total Tests Working | Delta Tests (number Added) | Delta Tests Working | Estimated Number of Required Tests | Estimated Number of Tests To Create | Estimated Fraction with no Test Coverage | Jira Open Issues Count | Jira In-progress Issues Count | Jira Resolved Issues Count | Jira Closed Issues Count
start swag | 2012-04-01 | 74 | 74 | 0 | 58 | 58 | 0 | 100 | 0 | 100 | 232 | 132 | 100 | 0 | 0 | 2000 | 1768 | 88.4% | 85 | 2 | 25 | 11
2012-04-20-s1 | 2012-04-20 | 74 | 69 | 5 | 58 | 58 | 0 | 124 | 18 | 106 | 256 | 145 | 111 | 24 | 11 | 2200 | 1944 | 88.36% | 97 | 2 | 36 | 11
Fiction (replace with real data at end of next spin) |  | 74 | 59 | 15 | 58 | 52 | 6 | 150 | 18 | 132 | 282 | 154 | 128 | 26 | 17 | 2200 | 1918 | 87.18%
Fiction (replace with real data at end of next spin) |  | 74 | 49 | 25 | 58 | 40 | 18 | 160 | 12 | 148 | 292 | 101 | 191 | 10 | 63 | 2200 | 1908 | 86.73%